## Sheet1
Work Category | AH functionality | Epic/Feature IDs | CVS Dependency | CVS API Availability | Aetna Dependency | AH Target Date |  | Notes | Savings/Benefit
[6 empty] | Web | Native
i90 Migration Baseline | RX List | F177296: Rx: Web: i90 Migration Baseline: Prescription List Redesign F196282: Rx: iOS: i90 Migration Baseline: Prescription List Redesign F214197: Rx: Android: i90 Migration Baseline: Prescription List Redesign | CVS PLP i90 API | Available now | N/A | PI3 | PI4 | All these must be completed together before releasing to production.
| RX Details (Includes Auto Refill and Ship Consent) | E26427: Rx: i90 Migration Baseline: Redesign - RX Details i90 PDP Migration Updates (Web Only) F146712: Rx: iOS: i90 Migration Baseline: Prescription Details Page F146713: Rx: Android: i90 Migration Baseline: Prescription Details Page | CVS PDP i90 API CVS Ship Consent i90 API Auto Refill | All Available now | N/A | PI3 | PI3
| Place Order | F217490: Rx: iOS: i90 Migration Baseline: Update Place Order API call F217491: Rx: Android: i90 Migration Baseline: Update Place Order API call | CVS Place Order i90 API | Available now? | N/A | PI3? | PI3
| RX Dashboard | F190214: Rx: Web: i90 Migration Baseline: RX Dashboard updates F202208: Rx: iOS: i90 Migration Baseline: RX Dashboard updates F217933: Rx: Android: i90 Migration Baseline: RX Dashboard updates | N/A | N/A | Server/UI Updates | PI3? |  |  | We'll need Server and UI updates to stop using the Aetna BFF
RX Self Service | Cancel In-flight Prescription | F214022: Rx: Web: Cancel In-flight Order ⭐️⭐️⭐️ F214024: Rx: iOS: Cancel In-flight Order ⭐️⭐️⭐️ F214026: Rx: Android: Cancel In-flight Order ⭐️⭐️⭐️ | CVS Cancel Eligibility i90 API | Available now | i90 Migration Baseline | PI4 |  |  | (327,296 calls) $490,944 annual savings
| Update Existing Order | F214008: Rx: Web: Update Fill Date ⭐️⭐️⭐️ F214010: Rx: iOS: Update Fill Date ⭐️⭐️⭐️ F214012: Rx: Android: Update Fill Date ⭐️⭐️⭐️ | CVS Change Fill Date i90 API | Available now for AH to request experience, CONFIRMING TIMELINE | i90 Migration Baseline |  |  |  | (386,613 calls) $579,915 annual savings
| Correct Payment Issues | F167032: Rx: Web: Release Payment Holds ⭐️⭐️⭐️ F209934: Rx: iOS: Release Payment Holds ⭐️⭐️⭐️ F209936: Rx: Android: Release Payment Holds⭐️⭐️⭐️ | CVS Change Payment Method i90 API | Available now | i90 Migration Baseline | PI4 |  |  | (659,397 calls) $989,095 annual savings
| Archive (Hide) Prescription | F186827: Rx: Web: Hiding/Archiving Medications ⭐️⭐️⭐️ F214113: Rx: iOS: Hiding/Archiving Medications ⭐️⭐️⭐️ F214114: Rx: Android: Hiding/Archiving Medications ⭐️⭐️⭐️ | CVS Archive RX i90 API | Available now | i90 Migration Baseline |  |  |  | Caremark.com sees about 10-12K weekly visits where members utilize this functionality (about 3% of total weekly visits to the Prescription Detail Page or 132,094 YTD
Transfers | CVS retail to CVS mail order | TBD | CVS i90 API, Updates to back end support for transfers | Client availability planned for Q3 per April DDAT PS roadmap | i90 Migration Baseline
| CVS mail order to CVS retail | TBD | CVS ??? I90 API | Available now for AH to request experience, CONFIRMING TIMELINE | i90 Migration Baseline
| CVS retail to CVS retail | TBD | CVS Change Fill Location i90 API | Available now for AH to request experience, CONFIRMING TIMELINE | i90 Migration Baseline
| Non-CVS retail to CVS mail | TBD | CVS ??? I90 API | Client availability planned for Q3 per April DDAT PS roadmap | i90 Migration Baseline
| Non-CVS mail to CVS retail | TBD | CVS ??? I90 API | Client availability planned for Q3 per April DDAT PS roadmap | i90 Migration Baseline
| Non-CVS retail to non-CVS retail | TBD | CVS ??? I90 API | Experience available to clients in late 2025 per April DDAT PS roadmap | i90 Migration Baseline
| CVS mail/retail to non-CVS retail | TBD | CVS ??? I90 API | Experience available to clients in late 2025 per April DDAT PS roadmap | i90 Migration Baseline
Note on A11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Kerz, Leslie and @Hahn, Shawn I see Q3 and late 2025 timelines for the in flight work that Caremark has. Even if they delivered these on time, it appears to me that we don't have a path forward to delivering in 2025 within Aetna Health. Is that right? Reply: @Brucker, William if you mean 4Q client? No we don’t at this time. Falcon is targeted 1Q 2026
Note on E11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Hahn, Shawn what is actually being delivered is the Fast Start version. Right? Then we need them to build the automated version? Reply: Yessir. I did call that out in the CVS Dependencies column, but maybe it wasn’t clear?
Note on E12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Hahn, Shawn since these are available now, we can connect to them once we have the strategy for how we integrate with i90? Reply: We do need to request for the experience to be created for Aetna. Which requires an intake. Will do that tomorrow.
Note on E14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Hahn, Shawn are these Fast Start only or do they need requirements to build the automated versions? Reply: According to the roadmap, this is a transfer, though I need to confirm the timing. Q3 may only be the backend changes. Will do that.